## Gantt Data
Task | Section | Schedule | Start Date | End Date | Duration (days) | Start Shift (days) | End Shift (days)
New DTR Development | Development | Current | 2026-08-03 | 2026-11-10 | 100
New DTR Development | Development | Proposed | 2026-08-03 | 2026-11-10 | 100 | 0 | 0
PAS with DTR Development | Development | Current | 2026-08-12 | 2026-11-10 | 91
PAS with DTR Development | Development | Proposed | 2026-08-12 | 2026-11-10 | 91 | 0 | 0
NEW DTR - Redirecting to PAS response (Internal E2E) | E2E & Testing | Current | 2026-10-05 | 2026-10-09 | 5
NEW DTR - Redirecting to PAS response (Internal E2E) | E2E & Testing | Proposed | 2026-10-05 | 2026-10-09 | 5 | 0 | 0
Client UAT NEW DTR - Redirecting to PAS response | E2E & Testing | Current | 2026-10-12 | 2026-10-16 | 5
Client UAT NEW DTR - Redirecting to PAS response | E2E & Testing | Proposed | 2026-10-12 | 2026-10-16 | 5 | 0 | 0
PAS for Internal E2E validation (with CES & HOS) | E2E & Testing | Current | 2026-10-16 | 2026-11-13 | 29
PAS for Internal E2E validation (with CES & HOS) | E2E & Testing | Proposed | 2026-10-16 | 2026-11-13 | 29 | 0 | 0
PAS Client UAT start date with complete scope | UAT & Deployment | Current | 2026-11-10 | 2026-11-27 | 18
PAS Client UAT start date with complete scope | UAT & Deployment | Proposed | 2026-11-10 | 2026-11-27 | 18 | 0 | 0
Go Live | UAT & Deployment | Current | 2026-11-28 | 2026-11-28 | 1
Go Live | UAT & Deployment | Proposed | 2026-11-28 | 2026-11-28 | 1 | 0 | 0
How to use this sheet:
Edit the yellow 'Proposed' Start/End Date cells to model a new schedule.
Start Shift / End Shift show the difference (days) vs. the Current schedule (positive = later, negative = earlier).
The Gantt Chart tab shows Current bars in blue and Proposed bars in orange for direct comparison.

## Gantt Chart
Legend: | Current | Proposed